## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Rishika Burnwal | 2026-08-31 | PDF and DOCX files were initially not processed correctly due to document extraction library/import issues. | Sprint 1 | Rishika Burnwal | Maintainability | Installed the required libraries and corrected the document extraction modules for PDF and DOCX files. | 2026-08-31 | Closed | PDF and DOCX extraction working correctly.
2 | Rishika Burnwal | 2026-08-31 | Empty or unreadable documents caused processing problems. | Sprint 1 | Rishika Burnwal | Logical | Added validation to check extracted text before chunking and embedding generation. | 2026-08-31 | Closed | Invalid input handled correctly.
3 | Rishika Burnwal | 2026-09-01 | Embedding generation failed because of a missing Torchvision dependency. | Sprint 1 | Rishika Burnwal | Maintainability | Installed the required dependency and verified embedding generation. | 01-Sept-26 | Closed | Embeddings generated successfully.
4 | Rishika Burnwal | 2026-09-02 | Search button caused a duplicate Streamlit element ID error. | Sprint 1 | Rishika Burnwal | User Interface | Added a unique key to the Search Knowledge Base button. | 2026-09-02 | Closed | Duplicate element error resolved.
5 | Rishika Burnwal | 2026-09-02 | ChromaDB count represented chunks rather than unique uploaded documents. | Sprint 1 | Rishika Burnwal | Logical | Added source filename metadata to chunks and implemented unique document counting. | 2026-09-03 | Closed | Testing metadata-based document count.
6 | Rishika Burnwal | 2026-09-10 | Groq LLM integration initially failed because the configured LLM model was unavailable. | Sprint 2 | Rishika Burnwal | Maintainability | Replaced the unavailable model with a supported Groq model and tested the API connection. | 2026-09-08 | Closed | Groq LLM integration working successfully.
7 | Rishika Burnwal | 2026-09-15 | Multiple uploaded documents were initially processed using single-file processing logic. | Sprint 2 | Rishika Burnwal | Logical | Updated the processing pipeline to iterate through all uploaded documents and store each document's chunks in ChromaDB. | 2026-09-14 | Closed | Multiple documents processed and stored successfully.
8 | Rishika Burnwal | 2026-09-28 | Project health score was initially difficult to interpret without a clear risk/status representation. | Sprint 3 | Rishika Burnwal | User Interface | Added health status classification and graphical representation for overall project health. | 2026-09-27 | Closed | Health dashboard improved
9 | Rishika Burnwal | 2026-09-30 | Documentation output was initially generated as a single combined document instead of separate project deliverables. | Sprint 3 | Rishika Burnwal | Logical | Implemented separate PDF generation for User Stories, Risk Register and Action Items. | 2026-09-29 | Closed | Separate PDF downloads added
10 | Rishika Burnwal | 2026-10-08 | Complete system testing identified issues requiring validation of document retrieval, all three AI agents, project isolation, health analysis, and PDF generation. | Sprint 4 | Rishika Burnwal | Logical | Tested all major features using project documents, verified agent responses against retrieved context, checked project-wise data isolation, and validated dashboard and PDF outputs. | 2026-10-07 | Closed | All tested features passed the final validation.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others